## Defect Log
ACCESSIBILITY QA — DEFECT TRACKING REGISTER
Document: WSF eLearning Module (WSF-2024-01) ¦ Standard: WCAG 2.1 A/AA ¦ Auditor: Bhushan Singh ¦ Date: May 2025
Defect ID | Page / Location | WCAG Criterion | Principle | Level | Severity | Issue Summary | Impact on AT User | Recommended Fix | Tool Used | Status | Owner | Target Date
DEF-001 | Pg 2 — Section 1 Heading | 1.3.1 Info & Relationships | Perceivable | A | High | Heading level skips H1→H3 with no H2 in between | Screen reader users cannot navigate by heading tree accurately; NVDA announces wrong level | Insert H2 heading 'Why Safety Matters' between existing H1 and H3, or promote H3 to H2 | NVDA, Manual Review | Open | Bhushan Singh | 15 May 2025
DEF-002 | Pg 2 — Grey italic note | 1.4.3 Contrast (Minimum) | Perceivable | AA | Critical | Body text colour #AAAAAA on white gives 2.32:1 contrast ratio (required: 4.5:1) | Users with low vision or colour blindness cannot read the note text | Change text colour to minimum #767676 (4.5:1) or recommended #555555 (7.0:1 — AAA) | MS Accessibility Checker, WebAIM Contrast Checker | Open | Bhushan Singh | 13 May 2025
DEF-003 | Pg 2 — Hyperlink | 2.4.4 Link Purpose (In Context) | Operable | A | High | Hyperlink anchor text reads 'click here' — no destination information provided | NVDA Links List (INSERT+F7) shows 'click here' only; blind users cannot determine link purpose | Change to 'OSHA Official Workplace Safety Guidelines' or 'Visit OSHA.gov — Safety Resources' | NVDA Links List, Manual Review | Open | Bhushan Singh | 15 May 2025
DEF-004 | Pg 3 — Hazard Types Table | 1.3.1 Info & Relationships | Perceivable | A | Medium | Table header row styled visually but not programmatically marked as 'Header Row' in Word | AT users hear column data without hearing the column header association; table is harder to understand | Select header row → Table Design → Check 'Header Row' & 'Repeat Header Rows'. Verify TH tags in PDF export. | MS Accessibility Checker, NVDA | Open | Bhushan Singh | 22 May 2025
DEF-005 | Pg 3 — Figure 1 (Flowchart image) | 1.1.1 Non-text Content | Perceivable | A | Critical | Image (hazard identification flowchart) has no alt text — MS Checker reports error | NVDA announces: 'graphic, graphic' with zero informational content for the image | Add: 'Flowchart: 5-step hazard identification: Identify type → Assess risk → Rate risk → Select controls → Review' | MS Accessibility Checker, NVDA | Open | Bhushan Singh | 13 May 2025
DEF-006 | Pg 4 — IMPORTANT paragraph | 3.1.5 Reading Level / Best Practice | Understandable | AAA | Medium | All-caps warning text ('IMPORTANT: ALL EMPLOYEES...') may be read letter-by-letter by some screen readers | Users of older NVDA / JAWS versions experience 'I-M-P-O-R-T-A-N-T' read out individually — unintelligible | Use title case or sentence case with bold + colour emphasis. Apply Word 'All Caps' style if visual caps required. | NVDA (text-to-speech test) | Open | Bhushan Singh | 22 May 2025
DEF-007 | Pg 6 — Answer Key | 1.4.1 Use of Colour | Perceivable | A | Medium | Answer key uses green text as sole indicator of 'Correct' — no text-based label or icon provided | Users with red-green colour blindness (deuteranopia) cannot distinguish answer key from normal text | Prefix answers with text: 'Correct Answer — Q1: C ¦ Q2: B ¦ Q3: 24 hours'. Remove colour-only cue. | Manual Review, Colour Blindness Simulator | Open | Bhushan Singh | 22 May 2025
DEF-008 | Document Metadata / File Properties | 3.1.1 Language of Page | Understandable | A | Low | Document language not declared in file properties / metadata | Screen readers may apply incorrect pronunciation rules; TTS may use wrong language phonetics | File → Options → Language → Set Editing Language to 'English (United Kingdom)' | MS Accessibility Checker | Open | Bhushan Singh | 29 May 2025

## Dashboard
ACCESSIBILITY AUDIT — QA DASHBOARD
WSF-2024-01 ¦ Auditor: Bhushan Singh ¦ Status: In Progress ¦ March 2026
Total Issues |  | Critical |  | High |  | Medium | Low/Info
8 |  | 2 |  | 2 |  | 3 | 1
Severity | Count |  | Status | Count | Principle | Count
Critical | 2 |  | Open | 8 | Perceivable | 5
High | 2 |  | In Review | 0 | Operable | 1
Medium | 3 |  | Resolved | 0 | Understandable | 2
Low | 1 |  | Closed | 0 | Robust | 0
Info | 0

## Remediation Tracker
REMEDIATION PROGRESS TRACKER
Defect ID | Issue (Short) | Priority | Assigned To | Target Date | Completion Date | Effort (hrs) | Verified By | Notes
DEF-002 | Contrast: grey text | P1 — Immediate | Bhushan Singh | 13 May 2025 |  | 0.5 |  | Change #AAAAAA to #555555
DEF-005 | Alt text: flowchart | P1 — Immediate | Bhushan Singh | 13 May 2025 |  | 0.5 |  | Write descriptive alt text for flowchart
DEF-001 | Skipped heading H1→H3 | P2 — High | Bhushan Singh | 15 May 2025 |  | 0.5 |  | Insert H2 or promote H3
DEF-003 | Link text: 'click here' | P2 — High | Bhushan Singh | 15 May 2025 |  | 0.25 |  | Replace with 'OSHA Safety Guidelines'
DEF-004 | Table header markup | P3 — Medium | Bhushan Singh | 22 May 2025 |  | 1.0 |  | Enable Header Row in Table Design
DEF-006 | All-caps warning text | P3 — Medium | Bhushan Singh | 22 May 2025 |  | 0.5 |  | Convert to title case + bold
DEF-007 | Colour-only answer key | P3 — Medium | Bhushan Singh | 22 May 2025 |  | 0.5 |  | Add 'Correct:' text prefix
DEF-008 | Document language | P4 — Low | Bhushan Singh | 29 May 2025 |  | 0.25 |  | Set editing language in Word options